## Slide 1: Mid-term Quality Evaluation Report of UZDOC2.0 Conclusions and key issues to be decided
Prof. Eva Orosz
On behalf of ELTE-Team
Consortium meeting
Tashkent Financial Institute, October 1, 2018

## Slide 2: Objectives of internal quality assurance (IQA)
To contribute with the specific tools of QA to the timely progress and implementation of the work plan, to achieve the specific objectives (SO 1-4), the milestones (M1-M14) and the deliverables (D)
IQA is a responsibility shared by all partners.
  ELTE functions as the work package coordinator; supported by KARSU

## Slide 3: Activities of internal quality assurance
Internal QA Plan developed and circulated among the UZDOC-partners
Template of Evaluation Questionnaire to be filled in by Uzbek participants developed
Evaluation Questionnaires (EQs) were filled at the job-shadowing (Turin) and QA Workshop, Seminar and Training (Tashkent)
(A): EQs were processed and reports produced
Outline was prepared for the (Self-)Evaluation Reports to be prepared by the responsible organizations
(B): Internal Evaluation by responsible organizations made (POLITO) /under preparation (UGR)
Evaluation reports of events (combining (A), (B) and ELTE comments) prepared (or under preparation)
Mid-term Internal Quality Assurance Report (October 15, 2016 – March 15, 2018) has been prepared

## Slide 4: Evaluation of the UZDOC 2.0 events by Uzbek participants (Professional content of the events as a whole)
 | Very useful | Useful | Mean Max=4
Job shadowing in Turin, October 2017 |  |  | 3.5
Quality Assurance Consultation Workshop (Excercise in designing a model JDP), February 2018 | 81% | 19% | 3.8 (3.8)
Quality Assurance Seminar, February 2018 | 64% | 36% | 3.6
Training for doctoral candidates and supervisors, Tashkent, February 2018 | 50% 53% | 50% 47% | 3.5 3.5

## Slide 5: Internal Quality Assurance Evaluation Report (October 15, 2016 – March 15, 2018)
Key elements
Effects of new reform (February 2017) and ongoing changes in Uzbek doctoral education on the deliverables of the project
Snapshot of the current status of implementation of milestones and deliverables
Summary of evaluation reports of the events organised so far

## Slide 6: Main conclusions
Most of the project activities envisaged for the report-period have been successfully implemented
Uzbek participants found these activities useful from the point of view of their activity
Due to new reform and changing legislation in Uzbek doctoral education, some elements of the work plan requires modification.
The plan for the establishment of Joint Doctoral Centre has been replaced by the goal of a virtual network of (regional) centres for doctoral education.
The goal of elaboration of a Joint Doctoral Programme by the end of the project also requires reconsideration

## Slide 7
Outputs (tangible) and Outcomes (intangible): | Progress / Evaluation
WP1 | 
D1.1. Optimized work plan | Some modifications were needed due to new reform
WP2 | 
D2.1. Developed Joint Doctoral Centre implementation guidelines | Modification of D2.1. to be clarified (in a written form)
D2.2. Established Joint Doctoral Centre in Uzbekistan | The necessary modification of D2.2. to be clarified (in a written form)
D2.3. Shared best practices between European and Uzbek partners on doctoral education | POLITO – May 15, 2018 ELTE – 2019 ( date to be decided)
D2.4. Raised awareness on quality assurance in doctoral education | QA Consultation workshop (Tashkent, February 5-6, 2018) Overall satisfaction*: 81% + 19% (3.8 /max:4) QA Seminar (Tashkent, February 7-8, 2018) Overall satisfaction*: 64%+36% (3.6 /max4)

## Slide 8: Main conclusions
Outputs (tangible) and Outcomes (intangible): | Progress / Evaluation
D2.5. Performed exercise in creating a model of a new joint doctoral programme | Exercise in the designing of a model of JDP made (Quality Assurance Consultation workshop) - Remaining part of D2.5 requires reconsideration due to changing legislation and due to the fact that the JDC will not be established
D2.6. Developed and performed trainings for supervisors, administrative staff and doctoral candidates | The 1st Training for students and supervisors was held on February 8-9, 2018 Overall satisfaction*: 53% + 47% (3.4/max:4)
 | 2nd Training to be held on (TBD)
D2.7. Developed and performed job shadowing events | 1st Job shadowing event was organized (Turin, October 9-13, 2017) Overall satisfaction: 60%+40% (3.5 /max:4)
 | 2nd Job shadowing event to be organized by UGR on (TBD)
D2.8. Raised awareness on the need for career development and career planning for doctoral candidates | Recommendations on career planning and career development of doctoral candidates to be developed One round table with business and industry sector to be organized (Tashkent, October 2018)

## Slide 9: To be decided: how to accomplish the remaining part of WP 2. D: 2.5. Performed exercise in designing a model of a new joint doctoral programme (JDP)
To be decided:
Option(A): to develop a JDP in chemistry
Option (B): to develop a consortium agreement for cooperation between 2 or more Uzbek UZDOC Partners in a specified doctoral programme
Option (C): to elaborate recommendations for
cooperation among Uzbek HEIs concerning doctoral education; and
cooperation with foreign HEIs concerning co-tutelle programme
Simulation exercise in the designing of a model of JDP was performed at the Quality Assurance Consultation workshop (Tashkent, 5 – 6, February 2018)
Responsible HEI: ELTE
D2.5 envisages the elaboration of a model JDP by the end of the project
Responsible HEIs: UGR + Uzbek partners
This goal requires reconsideration due to changing legislation and due to the fact that the JDC will not be established.

## Slide 10: Description of WP 2. D: 2.5. in the Project Plan
A goal of this deliverable is to put into practice the new approaches and tools for assuring the quality of doctoral Education […] by performing an exercise in designing a model of a new, joint doctoral programme.
This simulation of a joint doctoral programme will include all Uzbek HEI project partners.
Members of the newly established JDC will participate in the activity, further developing their skills and expertise in the area of doctoral education and learning how to create a new doctoral programme.

## Slide 11: Description of WP 2. D: 2.5. in the Project Plan
Fine-tuning and adjustments of the programme developed through exercise will take place during the consortium meetings and the ULCB meetings in Uzbekistan.
The draft of the programme will be made available on the web pages of the project, so every project partner will have an open
access to it for comments, modification and uggestions.
Deliverable is expected to be finished by the end of the project, and will be presented as part of the Final event in Month 35.